## Slide 1: Automatic Generation of 3D Environment Models from Robot Sensor Data
Tom-Ole Korbach
Anton Wagner

## Slide 2
1
2
3
4
Introduction
Current Approach
Current Progress
Timeline

## Slide 3: Introduction
1

## Slide 4: Introduction
Automatic Generation of 3D Environment Models from Robot Sensor Data
Useful for:
  Robotics
  Mapping
  Digital Twins
Possible Sensors:
  Cameras
    Color
    Depth
  LiDAR
  …
Raw sensor data != usable 3D model
Existing pipelines are:
  Complex
  Not fully automated
https://capsulesbot.com/blog/2018/06/11/robotics-projects.html

## Slide 5: Current Approach
2

## Slide 6: Current Approach

## Slide 7: Current Progress
3

## Slide 8: Current Progress
Researched Algorithms and Techniques
Understanding the Spot SDK
Started Data pipeline
  Getting Camera/Image data
  Recording Paths
  Running Paths
For Presentation purpose:
Brightness: +40% Contrast: -40%

## Slide 9: Timeline
4

## Slide 10: Timeline
Chart: 
| Literature Review | Data Collection | Data Preprocessing | Colmap | Gaussian Splat | Data Postprocessing | Thesis Writing | Thesis
Start Date | 46114 | 46127 | 46152 | 46158 | 46180 | 46210 | 46231 | 46114
Duration | 38 | 25 | 52 | 26 | 30 | 21 | 64 | 181

## Slide 11: Questions?
5